## Sheet1
Work Plan: STEPs4GROWTH (High-Level Tasks, Deliverables and Milestones in support of Project Goals and Objectives)
Note: more detailed Gantt Charts of Goals, Objectives, and Tasks will be generated by each CE Sectoral Partnership and Cross-Sector Thrust to augment this high-level Work Plan
Goals/Objectives | Pre-award Summer 2022 | 2022 | 2023 |  |  | 2024 |  |  | 2025 |  |  | 2026
|  | Fall | Spring | Summer | Fall | Spring | Summer | Fall | Spring | Summer | Fall | Spring | Summer | Fall
Overall High-level Plan |  | System Development
Program Design, with some Alpha/Beta implementation
Program Implementation, Rollout in 4 Regions, Replication of all curriculum and hands-on training in all 4 Regions
Goals for Vertical CE Sectors by Phase
SysDev: Backbone Orgs establish CE sectoral partnership teams, meetings, reporting | Establish work team: Backbone Lead; WDBs; CCs; RTCs; CoC; SSSs & Wrap-around services; Industy partners
SysDev: Produce a CE sectoral education/experience Pyramid model for each CE Sector (core and variations) | Define the curriculum that works for each CE Sector; and align with other CE sectors; Define hands-on training needs
SysDev: Define the curriculum development and equipment needs for ProgDes phase |  | Define the course curriculum to be implemented at CCs and RTCs
SysDev: Prepare for Alpha Testing in Summer 2023 in each Region |  |  | Plan for Alpha Test in each CE Sector
SysDev: Alpha Testing |  |  |  | Run Alpha Testing (~100 future CE Good Job placements)
ProgDes: Detail the process of delivery of curriculum and experimental training for each CE Sector |  |  |  | Plan for each Regions implementation with primary focus on one CE Sector; Improve on Alpha Tests; detail on-line and hands-on curriculum
ProgDes: Purchase training equipment for each Region (for one of the four CE Sectors) |  |  |  |  | Outfit the RTC in each Region with hands-on equipment and associated curriculum for their CE Sector
ProgDes: Prepare for Beta Test in Summer 2024 in each Region; do Beta Testing | [5 empty] | Plan for Beta Test in each CE Sector | Run Beta Tests (1 CE Sector Curriculum in each region), ~240 future CE Good Job placements
ProgImp: Prepare for implementation of full set of 4 CE Sector Pyramid Models in each Region | [6 empty] | Plan to implement the full set of CE Sectoral Pyramid Models in each region. Determine who/what will be taught on-line, if additional equipment will be needed for course hands-on training. Collaborate with all horizontal cross-sector thrusts to ensure alignment, reduce costs.
ProgImp: Ramp up for full cohorts of CE workers in each Region to take full spectrum of pre-apprenticeship training; Run Pilot #1; Plan and Run Pilot #2 | [7 empty] | Purchase equpment for 4 CE Sector training in RTCs, and for 2 mobile training units. |  | Run 4-CE-sector Pilot #1 in 4 regions (1000 CE Good Job placements) | Evaluate Pilot #1, improve, plan for Pilot #2 |  | Run 4-CE-sector Pilot #2 in 4 regions (1500 CE Good Job placements)
Goals for Horizontal Cross-Sector Thrusts by Phase
SysDev: DEIA, build Team and work with CE sectors |  | Draft a DEIA statement/policy
ProgDes: DEIA |  |  |  | Incorporate DEIA across CE Sectors fairly, include Autism
ProgImp: DEIA | [6 empty] | Collect Data and Report on meeting goals, improve from Beta Testing to Pilot #1 to Pilot #2
SysDev: Wrap-around Services, build Team and work with CE sectors |  | Growth Sector works with 4 regions to hire SSS, train SSSs, JFF to build wrap-around support
ProgDes: Wrap-around Services |  |  |  | Wrap-around support in 4 regions; Beta Test
ProgImp: Wrap-around Services | [6 empty] | Full wrap-around support system in place to support Pilot #1 and #2, SSSs guiding all future CE workers and collecting tracking data
SysDev: Recruiting, build Team and work with CE sectors |  | ApprenticeshipNC forming connections into all HSs in regions, future CE workers recruited for Alpha Test, working with Verticals to recruit more industry partners
ProgDes: Recruiting |  |  |  | Recruiting system using social media built in all 4 regions, full cohorts recruited for Beta Testing, recruiting of 50% of 1000 CE industries completed
ProgImp: Recruiting | [6 empty] | Recruiting system established to bring in 1500+ CE workers/yr using social media, WDBs, HS outreach. Recruiting of 80% of 1000 CE industries completed (with commitments to hire trained workers).
SysDev: Job Placement, build Team and work with CE sectors |  | All regions and CE Sectors trained and using Job Placement software
ProgDes: Job Placement |  |  |  | Linking of workers with employers working effectively using Job Placement software
ProgImp: Job Placement | [6 empty] | All CE industry partners are able to attract skilled workers to apprenticeship/internship/OJT opportunities
SysDev: Core Curriculum, build Team and work with CE sectors |  | Establish core curriculum across 4 CE sector in Pyramid Model
ProgDes: Core Curriculum |  |  |  | Verify and improve core curriculum in 4 CE sectors, and establish the curriculum and trainers
ProgImp: Core Curriculum | [6 empty] | Install a system where all future CE workers across all 4 regions can take core curriculum courses on-line, and have access to hands-on labs
SysDev: Hands-on Training, build Team and work with CE sectors |  | Establish hands-on curriculum across 4 CE sector in Pyramid Model
ProgDes: Hands-on Training |  |  |  | Verify and improve hands-on curriculum in 4 CE sectors, and establish the curriculum and trainers. Also put in place needed labs for future CE workers to learn.
ProgImp: Hands-on Training | [6 empty] | Install a system where all future CE workers across all 4 regions can take hands-on training courses with access to hands-on labs
SysDev: Innovative Technology, build Team and work with CE sectors |  | Technology thrust works with verticals to define prioritized research needs for each sector
ProgDes: Innovative Technology |  |  |  | CEPDAM works with vertical CE sectors to establish approach to research and technology that can be incorporated into Pyramid Model
ProgImp: Innovative Technology | [6 empty] | Research and Technology development course curriculum and lab training is incorporated into Pyramid Models for forward looking technology needs in CE sectors
SysDev: Battery and Storage, build Team and work with CE sectors |  | Battery needs from each CE sector are defined and differenctiated
ProgDes: Battery and Storage |  |  |  | Specialized battery and storage curriculum is developed for each Vertical CE sector, used in Beta Testing
ProgImp: Battery and Storage | [6 empty] | Battery and Storage training curriculum and hands-on training is established in each CE sector and available to all future CE workers in STEPs4GROWTH
SysDev: Expansion, build Team and work with CE sectors |  | A sustainability strategic plan is developed that includes access to additional funds from Federal Agencies and Industry
ProgDes: Expansion |  |  |  | Proposals submitted to Federal Agencies for additional funding for CE sector workforce development. Industry approached with a funding approach that would sustain STEPs4GROWTH beyond the EDA funding period
ProgImp: Expansion | [6 empty] | Establish a sustainability model that can support 1500+ CE workers/year.
SysDev: Advisory Boards, build Team and work with CE sectors |  | Build a diverse and well-represented EAB, meet once
ProgDes: Advisory Boards |  |  |  | Convene IAB once, and EAB once using an ISO9001 Mgt Mtg template to define improvements in the STEPs4GROWTH plans
ProgImp: Advisory Boards | [6 empty] | Convene IAB once, and EAB in Spring 2025 and 2026 using an ISO9001 Mgt Mtg template to define improvements in the STEPs4GROWTH plans
Milestones (due at end of period Shown); Details to be found in the Milestones and Deliverables Chart |  | M1 | M2, M3, M3.1, M3.2, M3.3 |  |  | M4, M5, M5.1, M5.2, M5.3, M5.4, M5.5, M5.6 |  |  | M6, M6.1 |  |  | M7
Deliverables (due at end of period shown); Details to be found in the Milestones and Deliverables Chart | D0 |  | D1, D1.1, D1.2, D1.3, D1.4, D1.5, D1.6 |  | D2, D2.1 | D3, D3.1, D3.2, D3.3, D3.4 |  | D3.5, D3.6, D3.7, D3.8, D4, D4.1 | D5, D5.1 |  | D6, D6.1, D6.2, D6.21, D6.3, D6.4 | D6.5 |  | D7, D7.1, D7.2, D7.3, D7.4
Required QUARTERLY DOC EDA GJC Reporting: Financial Status Report; Performance Report |  | none due | 15Feb 1QY1 reports and 15May 2QY1 reports | 15Aug 3QY1 reports | 15Nov 4QY1 reports | 15Feb 1QY2 reports and 15May 2QY2 reports | 15Aug 3QY2 reports | 15Nov 4QY2 reports | 15Feb 1QY3 reports and 15May 2QY3 reports | 15Aug 3QY3 reports | 15Nov 4QY3 reports | 15Feb 1QY4 reports and 15May 2QY4 reports | 15Aug 3QY4 reports | 15Nov 4QY4 reports; Final Post-Project Status Report (June2027)
LEGEND:
Task: On time, on budget
Task: Moderate risk of completion, mitigation plan may be required
Task: High risk of completion, mitigation plan required